## Sheet1
Item Number | WBS ITem Name | Description | Predecessor | Resources | Comments
1 | Traffic Flow AI Algorithms | To develop AI for managing traffic, we start by collecting a lot of traffic data. We use Python, with libraries like Pandas and NumPy, to clean and prepare the data. This step makes sure that our machine learning models, which we build using TensorFlow and PyTorch, get good-quality data to work with. Our main goals are to predict traffic flow and make traffic lights smarter by adjusting them in real time. We plan to use time-series forecasting to predict traffic and Q-learning to make traffic lights more adaptive. To test our models, we'll use a program called SUMO (Simulation of Urban MObility). This package lets us run tests in different situations before we use the models in production. Once everything is tested, we will connect the AI models to the traffic control system through RESTful APIs. This way, the AI can easily communicate with the traffic lights and other hardware devices. We plan to also use Docker containers to help us deploy our models on servers easily, making sure we can scale up without too much trouble.
1.1 | Identify Data Sources for Traffic Flow | Assess various sources of traffic data, including government traffic flow databases, real-time sensor feeds, and historical traffic patterns to ensure a robust dataset for analysis. | None | Peyton Garcia Avery Johnson
1.2 | Develop Data Collection Scripts in Python | Design and implement Python scripts leveraging libraries such as Requests or BeautifulSoup for web scraping, and APIs for structured data collection, ensuring comprehensive and automated data retrieval. | 1.1 | Riley Davis Morgan Miller Taylor Davis
1.3 | Execute Data Collection from Multiple Sources | Execute the Python scripts to systematically collect traffic data, ensuring a broad and diverse dataset that includes peak, off-peak, and event-driven traffic conditions for accurate modeling. | 1.2
1.4 | Clean Data using Pandas for Missing Values | Utilize Pandas and NumPy for data cleansing, including handling missing values, outlier detection, and normalization. Prepare the dataset for analysis by structuring it in formats suitable for machine learning models. | 1.3
1.5 | Normalize and Augment Data | Apply statistical methods to normalize data for consistency, and use augmentation techniques such as synthetic data generation to enhance model training, especially in underrepresented traffic scenarios. | 1.4
1.6 | Train and Validate Time-Series Forecasting Model | Construct a machine learning model using TensorFlow for time-series forecasting of traffic flow. This includes feature selection, model training with cross-validation, and hyperparameter tuning to optimize prediction accuracy. | 1.5
1.7 | Implement and Test Q-Learning Model | Implement a reinforcement learning model with PyTorch, designing a Q-learning algorithm to optimize traffic light timing based on real-time traffic conditions, enhancing traffic flow and reducing congestion. | 1.5
1.8 | Simulate Traffic Scenarios with SUMO | Validate the effectiveness and efficiency of the developed models using SUMO simulations, creating a variety of traffic scenarios to ensure the models can accurately predict traffic flow and adaptively control traffic signals under diverse conditions. | 1.6, 1.7
1.9.1 | Containerize AI Models with Docker | Package the AI models into Docker containers for ease of deployment and scalability. This step involves creating Dockerfiles, building images, and testing the containers to ensure that the models run efficiently in a virtualized environment. | 1.8
1.9.2 | Integrate AI Models with Traffic Control Systems | Deploy the Dockerized AI models and establish communication with the traffic control infrastructure via RESTful APIs. Ensure seamless data exchange and real-time decision-making capabilities. | 1.9
2 | IoT Traffic Sensors Installation | We will start by installing IoT traffic sensors in places we have determined to be best suited for traffic optimization using traffic data from ArcGIS. By doing this we enhance our coverage and improve our data. We plan to use a multimodal traffic monitoring platform with mmWave Radar beams to track traffic in real-time. These sensors will be connected through using available 5G networks to rapidly transfer data to our main traffic server allowing for large-scale, real-time traffic optimization decisions. We will ensure the sensors are installed up to code to preserve their longevity. Before we deploy, we will run comprehensive testing to ensure the data and network are reliable, using tools that mimic different traffic scenarios. This can include JUnit testing and other forms of unit tests depending on the languages we use. If tests pass, we'll continue to the next phase, where the system is officially up and running.
2.1 | Retrieve Traffic Light Maps for City | Get a Map of Every Traffic Light for selected city. Using this we can map out where mmWave radar sensors will need to go to get full coverage of each intersection. | none | Jordan Jones Avery Davis
2.2 | Get info on exisiting technology at each intersection | Collect data on all existing technology for each intersection to plan out what intersections will need to add cameras. | 2.1 | Quinn Clark
2.3 | Aquire Propers approvals and permitting from city | Will need to get our plans approved by the citys department of transportation as well as aquire any necessary permits to install our technology. | 2.1, 2.2 | Reagan Bell Reagan Murphy
2.4 | Purchase adaquate Technology | Once we have mapped out the entire city we can then buy an adaqute number of mmWave Radar Sensors and Traffic cameras to cover the city. | 2.2, 2.3
2.5 | Get info on 5G networks in the area | Work with a Network Service Provider who can provide us with city wide reliable coverage. This will be important in connecting all of the IoT devices to our central servers to allow for our large scale real time processing. | none | Alex Williams Jordan Williams
2.6 | Installation | Work with local contractors, engineers, and the city to install out sensors and new cameras city wide. Need to make sure everything is done to code and test throughly. | 2.3, 2.4, 2.5
2.7 | Connect all devices to network | Connect all IoT devices to the 5G network and ensure they are working and functioning properly. Make necessary replacements to defective sensors and cameras. | 2.6
2.8 | Comprehensive Testing | Comprehensive testing for all IoT devices ensuring their quality. Need to test different senarios to make sure the sensors have full and reliable coverage of every intersection. | 2.7
2.9 | Train AI Model | Train AI Model with real data from IoT Devices at each intersection to make final optimizations and ensure everything is working properly. | 2.8, 1.9.1
3 | Central Traffic Management Server | A strong server system is essential for setting up our traffic management center. We are going with 10 top-notch Dell PowerEdge servers. They have the latest Intel Xeon CPUs to handle data super fast and run on Linux with Apache for the best security and reliability. This setup is meant to deal with huge amounts of data, up to 50TB, from all over the city's traffic sensors. Our servers will not just analyze traffic with our AI software but also manage all the data from the IoT sensors, making real-time traffic decisions possible. We plan on regular maintenance to keep everything running smoothly, including updates and check-ups to ensure our system stays top-notch.
3.1 | Plan and Analyze Server Needs | Perform a detailed analysis of the needs for the STLS server. Server need to have the capacity, processing power, and data storage specs to handle up to 50 TB of city-wide traffic sensor data. | 2.1, 2.2 | Rory Clark Taylor Brown
3.2 | Purchase Server | Purchase 10 Dell PowerEdge servers equipoed with the latest Intel Xeon CPUs | 3.1
3.3 | Setup Server | Need To set up these servers and install Linux OS onto all servers. Using Linux due to its history of reliability and security features. Linux will server as a stable platform for running STLS traffic applications and services | 3.2
3.4 | Configure Network | Configure an Apache web server on the Linux systems. Apache will be used because of its robust security features and compatibility with Linux. This will provide a stable enviorment to run our STLS applications. | 3.3
3.5 | Setup Network Security Measures | Setup a secure and efficient network architecture for the servers. This includes setting up firewalls, VPNs, and other security measures to protect data transmission and access. Ensure the network is still optimized for high-speed communication with IoT traffic sensors. | 3.4
3.6 | IoT Sensor Data Management | Set up systems for receiving and managing data from IoT traffic sensors distributed throughout the city. This involves configuring network interfaces and protocols for high-speed data transmission and processing. | 2.7, 3.3
3.7 | System Testing | Conduct comprehensive testing of the server setup, including stress tests to simulate high traffic data loads. Verify that the servers can efficiently process and analyze data from up to 50TB of city-wide traffic sensors. | 3.6
3.8 | Regular Maintenance Schedule | Develop a maintenance schedule for regular updates and check-ups of the server hardware, operating system, and security measures. This schedule will ensure that the system remains operational, secure, and up to date. | 3.7
3.9 | Performance Monitoring and Optimization | Implement performance monitoring tools to continuously assess the servers efficiency. Analyze performance data to identify possible optimizations, ensuring the traffic management center operates smoothly for all traffic conditions. | 3.8
4 | Sensor and Camera Data Integration API | To make sure our IoT sensors and traffic cameras work effectively with our main traffic system, we are building an industry-grade API using the Django REST framework. We chose it because it's great at dealing with complicated data and works well with Python, which we use for all our backend material. This project is all about making a middle layer that can quickly send data from all the traffic sensors and cameras in the city to our server. This lets us make traffic decisions on the fly based on current information. We are focusing on making this API extremely fast, using async programming and caching so we can change traffic signals in short periods of time. We plan to test this API multiple times, using tools like Postman and LoadRunner, to make sure it can handle a lot of data when the city's traffic is at its busiest. |  | Kennedy Thomas Rowan Moore
4.1 | Define API Requirements | Determine the data format, frequency, and size of the payload from various sensor types. This will include the mmWave radar and infrared cameras. This will be used to establish endpoint specifications and data schema. Analyze the historical traffic data patterns to anticipate future data loads and structure the API for efficient data handling and querying capabilities. | 5.1 | Rowan Moore Skyler Wilson Skyler Moore
4.2 | Design API Architecture | Develop a high-level architectural design focusing on microservices to ensure scalability. The architecture should support concurrent data streams, web sockets and provide mechanisms for load balancing. This architectures ensures that the system can handle sudden spikes in data flow from city-wide sensor networks during peak traffic periods. We expect rush hours to be troublesome for data architecutres that cannot handle this type of work. | 4.1, 5.1 | Skyler Wilson Skyler Moore
4.3 | Optimize API for Performance | Utilize advanced programming techniques like non-blocking I/O and event-driven architecture to enhance the throughput of the API. Implement data caching strategies and optimize database interactions to reduce latency, especially during the real-time traffic data processing and analysis. | 4.1,4.2 | Alexis Taylor Emerson Martin Dakota Moore Skyler Anderson Alexis Martin
4.4 | API Testing | Execute comprehensive testing, including load testing to simulate real-world traffic conditions, ensuring the API can handle extensive data streams without performance degradation. This can include JEst, Junit, and all type of large testing modals. Employ security penetration testing to identify and mitigate potential vulnerabilities, safeguarding against cyber threats. | All 4's | Alexis Taylor Emerson Martin Dakota Moore
4.5 | Set up API Monitoring and Logging | Implement a robust monitoring solution to track API health, usage metrics, and performance indicators, using tools like Posthog. Establish detailed logging practices to capture and analyze API transactions, facilitating quick debugging and issue resolution. Tools like AWS cloudwatch can help with these cases. | 4.4 | Dakota Moore Skyler Anderson Alexis Martin
4.6 | Deployment and Integration | Plan and execute the deployment of the API on a cloud-based infrastructure (AWS or Azure) ensuring high availability and disaster recovery capabilities. Coordinate with system architects to integrate the API seamlessly with existing traffic management platforms, conducting thorough end-to-end system testing. Utilize tools like Postman and loadrunner for API test calling. | 4.5 | Alexis Taylor Emerson Martin
5 | Traffic Data Database | We are setting up an enterprise-level database to keep track of all kinds of traffic data, including real-time data. Including traffic levels on the roads, accidents, and traffic flows at different times and locations. We are using MySQL due to its scalability and reliability. This database is key for making quick traffic decisions and for planning how to improve the city's roads over time with the use of efficient query processing. We are giving a large amount of attention to security, encrypting stored data (with AES-256) and data being sent around (with SSL/TLS), and we will dynamically check for any security issues. Setting up this entity means getting servers ready, planning out the database structure and schema, and making sure we can quickly find and store data. This is crucial for keeping our traffic system fast and reliable.
5.1 | Define Database Requirements | Conduct a thorough analysis of the traffic data types, including real-time sensor outputs and historical traffic statistics, to determine the database schema, storage needs, and indexing strategies. This analysis should consider the data's velocity, variety, and volume to ensure the database can handle complex queries and large datasets efficiently. The scheme must be thoroughly changed. With AI modals changing database mid way through production would be detrimental. | 1.1,4.5 | Dakota Moore Skyler Anderson Alexis Martin
5.2 | Design Database Architecture | Develop a scalable and secure database architecture that supports high concurrency and rapid access to traffic data. This should include partitioning strategies to manage data growth effectively, replication mechanisms for high availability, and a disaster recovery plan to ensure data integrity and availability in case of system failure. | 5.1 | Dakota Moore Skyler Anderson Alexis Martin
5.3 | Implement Database in MySQL | Set up the MySQL database, configuring it for optimal performance with traffic data characteristics. This includes creating tables with appropriate data types, constraints, and indexes to support efficient data retrieval and storage, as well as designing stored procedures and triggers to automate common data processing tasks. | 5.2 | Dakota Moore
5.4 | Integrate Security Measures | Implement comprehensive security protocols, including AES-256 encryption for data at rest and SSL/TLS for data in transit, to protect against unauthorized access and data breaches. Regular security audits and compliance checks should be conducted to ensure the database adheres to industry-standard security practices. | 5.3 | Rowan Moore Skyler Wilson Skyler Moore
5.5 | Develop Data Ingestion and Integration Processes | Design and implement data ingestion pipelines to capture and integrate real-time and historical traffic data into the database. This should include mechanisms for data validation, transformation, and cleaning to ensure data quality and accuracy. | 5.4 | Rowan Moore Skyler Wilson
5.6 | Optimize Database Performance | Regularly analyze database performance metrics to identify and address bottlenecks. Implement indexing, query optimization, and database tuning techniques to enhance data access speeds and support efficient real-time traffic data analysis and reporting. Joining tables/views where necessary to help with visualization and query speed on this large table (embedding). | 5.5 | Rowan Moore Skyler Wilson
5.7 | Establish Data Backup and Recovery Procedures | Develop and implement robust backup and recovery procedures to protect the database against data loss. This should include regular backup schedules, off-site storage solutions, and tested recovery plans to ensure rapid restoration of data services in the event of hardware failure or data corruption. | 5.6 | Rowan Moore Skyler Wilson
5.8 | Database Testing and Validation | Conduct comprehensive testing of the database system, including stress testing under high-load scenarios and validation of data integrity and accuracy. Ensure that the database meets all functional requirements and performs optimally under varying traffic conditions | 5.7 | Dakota Moore Skyler Anderson Alexis Martin
6 | Public Reporting Mobile App | Our project focuses on giving the community a role in managing traffic by letting people use a mobile app to report traffic issues and see what's happening on the roads in real-time. We are building this app for both iOS and Android, using React Native to make sure it works well on both platforms. The app will have features like GPS to share exact locations, a connection with the central traffic system to exchange data in real-time, and alerts to keep everyone updated on traffic conditions. We will be doing many tests to make the app easy to use and reliable. Our goal is to get the community involved, which will help optimize traffic management through the use of crowd-sourced data from the people who are on the roads.
6.1 | Define App Requirements | Conduct a needs assessment by engaging with potential users and stakeholders to gather detailed requirements for the app, including core features like incident reporting, traffic alerts, and live traffic condition displays. This will ensure the app is user-centric and meets the community's needs for effective traffic management participation. | 2 | Rowan Moore Jordan Jones Avery Davis
6.2 | Design App User Interface and Experience (UI/UX): | Develop a user-centric design for the app, focusing on intuitive navigation, accessibility, and engaging visual elements. The design should facilitate quick and easy reporting of traffic incidents and viewing of traffic conditions, enhancing user engagement and satisfaction. | 2,6.1 | Rowan Moore Skyler Wilson
6.3 | Develop App Using React Native: | Implement the app using React Native for cross-platform functionality, ensuring a consistent and responsive user experience across iOS and Android devices. Integrate advanced features such as real-time GPS tracking, interactive traffic maps, and push notifications to keep users informed and engaged. | 6.2 | Rowan Moore Skyler Wilson
6.4 | Integrate with Traffic Management System: | Develop robust API connections to integrate the app with the central traffic management system, enabling real-time data exchange. This integration allows the app to display up-to-date traffic information and enables users to contribute to traffic monitoring and management effectively. | 6.3 | Rowan Moore Skyler Wilson
6.5 | Implement Advanced Features: | Incorporate advanced features like AI-driven predictive traffic conditions, user-reporting tools with photo and video upload capabilities, and personalized traffic alerts based on user preferences and travel patterns to enhance the app's functionality and user engagement. | 6.4 | Dakota Moore Skyler Anderson Alexis Martin
6.6 | App Testing and Quality Assurance: | Conduct thorough testing phases, including usability, performance, and security testing, to ensure the app's reliability and effectiveness. Utilize automated testing frameworks and conduct beta testing with real users to gather feedback and refine the app's features and performance. | 6.5 | Jordan Jones Avery Davis
7 | Traffic Light Hardware Upgrade | We are planning to update our traffic lights to work more effectively with our new traffic management system. This means putting in new smart controllers and communication components that can communicate and distribute information with our new AI system without any problems. We are going to upgrade traffic lights to make them more flexible and able to change based on what commuters report in the system. The upgrade will involve adding new hardware that lets the traffic lights understand and follow the AI system's instructions. We plan to purchase the new compatible hardware, install it, and then test it thoroughly to make sure it runs smoothly without causing any issues for drivers. This upgrade is a big step towards modernizing our traffic control system to adjust to traffic in real-time, providing drivers with a safer and smoother experience. | 6.6 | Reagan Bell Reagan Murphy
7.1 | Evaluate Current Traffic Light Systems | Conduct a comprehensive review of existing traffic light infrastructure to identify upgrade needs and compatibility with new smart controllers. | None
7.2 | Design Upgrade Plan | Develop a detailed plan for the traffic light system upgrade, including selection of smart controllers and communication components. | 7.1
7.3 | Select Smart Controllers and Communication Components | Choose the new smart controllers and communication components that will allow traffic lights to interface with the AI system. | 7.2
7.4 | Procure Hardware | Purchase the selected smart controllers and communication components necessary for the upgrade. | 7.3
7.5 | Develop Installation Guidelines | Create comprehensive guidelines for installing the new hardware in existing traffic light systems. | 7.4
7.6 | Train Installation Teams | Train the technical teams on the new hardware and the installation process to ensure a smooth upgrade. | 7.5
7.7 | Install New Hardware | Carry out the installation of smart controllers and communication components in traffic lights as per the developed guidelines. | 7.6
7.8 | Test and Calibrate Upgraded Systems | Perform rigorous testing and calibration of the upgraded traffic lights to ensure they work seamlessly with the AI system and meet all operational requirements. | 7.7
7.9 | Monitor and Optimize Post-Installation | Post-installation monitoring to ensure optimal performance and adjust settings as needed based on real-world conditions and feedback. | 7.8
8 | User and Administrative Web Interface | We are working on creating web interfaces for both regular users and system administrators, making it easier for everyone to interact with traffic data and controls. The public side of the system will let people see traffic in real time, report issues, and get alerts on what is going on around them. For administrators, there will be a dashboard to access a more in-depth look into traffic patterns, managing traffic signals, and watching the AI system. We will use React for a smooth user experience and Node.js for a strong backend. The admin side will also use GIS tech for detailed maps and planning. We plan to put a great amount of focus on security, with things like two-factor authentication and controls on who can access certain information and to keep the data safe.
8.1 | User and administrative interface design | Design the visual layout and user experience for both the end-users and administrators of the STLS. |  | Logan Lee Leslie Hernandez Blake Lee
8.2 | Program user and administrative inferface layout | Develop and arrange the visual elements and navigation paths for the system's user and administrative interfaces. | 8.1 | Logan Lee Leslie Hernandez Blake Lee
8.3 | Program user and administrative inferface functionality | Implement and code the operational aspects in Java, including buttons, forms, and interactive elements, for user and admin interfaces. | 8.1, 8.2 | Blake Lee Shawn Lee
8.4 | GIS integration | Incorporate GIS capabilities to enable real-time traffic and geographic data analysis within the Smart Traffic Light System. | 8.3 | Cameron Patel Shawn Lopez Shawn Lee
8.5 | 2FA security measures | Implement 2FA to enhance security for user and administrator logins. | 8.4 | Shawn Wright Drew Wright
8.6 | Interface testing | Conduct tests to ensure the user and administrative interfaces are responsive and free of errors. | 8.5 | Logan Lee Leslie Hernandez Blake Lee
8.7 | Security testing | Perform comprehensive security assessments to identify vulnerabilities and ensure the protection of data. | 8.6 | Shawn Wright Drew Wright
8.8 | Guidelines for installation | Create detailed instructions for the proper setup and deployment of the STLS, ensuring compatibility and performance. | 8.7 | Blake Lee Shawn Lee
8.9 | Monitor and optimize | Establish processes for ongoing monitoring of the system's performance and implement optimizations for efficiency. | 8.8 | Logan Lee Leslie Hernandez Blake Lee
9 | System Security and Data Protection | This stage is about building a solid security system for our traffic management. We are setting up top-notch encryption to keep data safe, strong firewalls to block cyber threats, and performing many tests to find any weak spots. We also plan to work with cybersecurity professionals to make sure we are doing everything right and staying up to date with security standards. Training our team on cybersecurity and legal importances is another large part of this, as is starting a security operations center (SOC) to watch out for any threats. This allows us to create the most optimally secure platform that is safe for people to use on a daily basis.
9.1 | Develop encryption algorithm | Design and implement encryption algorithms to secure data in transit and at rest. |  | Amelia Lopez Harper Martin
9.2 | Firewalls | Configure and maintain firewalls to protect the system from unauthorized access and cyber threats. | 9.1 | Ava Jackson Henry Thomas
9.3 | Testing | Conduct thorough security testing, including penetration testing and vulnerability assessments, to identify and alleviate potential security issues. | 9.1, 9.2 | Amelia Lopez Henry Thomas
9.4 | Develop control systems | Implement access control mechanisms to ensure that only authorized users can access certain data and system functionalities. | 9.3 | Amelia Lopez Harper Martin
9.5 | IDPS integration | Deploy IDPS solutions to monitor network activity for malicious attacks or policy violations and respond to those issues. | 9.4 | Alexander Taylor Ethan Anderson Noah Davis
9.6 | Secure authentication protocols | Enforce and strengthen 2FA protocols to verify the identity of users and admins. | 9.5 | Shawn Wright Drew Wright
9.7 | Data recovery and backup plans | Establish data backup procedures and disaster recovery plans to ensure data integrity and availability in the event of a breach or failure. | 9.6 | James Davis Noah Davis
9.8 | Security policies and compliance | Develop and enforce security policies, procedures, and compliance measures in line with industry standards and regulations. | 9.7 | Shawn Wright Drew Wright
9.9 | Security awareness and training | Implement a security awareness and training program to educate employees about security best practices, potential threats, and their roles in maintaining security. | 9.8 | James Davis Noah Davis | Training cannot begin until policies are made